## Sheet1
S.No | Module | Feature | Business Requirement | Frontend | Backend | Mobile | Database | QA | Priority | Status | Owner | Remarks
1 | Authentication | Login | Users should log in securely | Pending | Pending | Pending | Pending | Pending | High | In Progress | Team | Awaiting implementation
2 | Student Dashboard | Dashboard | view dashboard | Completed | Pending | Pending | Pending | Pending | High | Frontend Completed | Frontend | UI completed
3 | Attendance | Attendance Dashboard | View attendance Summary | Completed | Pending | Completed | Pending | Pending | High | Front & Mobile Completed | Frontend & Mobile | Waiting for backend APIs
4 | Attendance | Mark Attendance | Teacher marks attendance | Pending | Pending | Completed | Pending | Pending | High | Mobile Completed | Mobile | Backend pending
5 | Attendance | Attendance History | View attendance History | Pending | Pending | Completed | Pending | Pending | Medium | Mobile Completed | Mobile | Backend pending
6 | Assignment | Assignment Management | Manage assignments | Pending | Completed | Pending | Pending | Pending | High | Back & DB Completed | Backend | APIs completed
7 | Notification | Notification Management | Send notifications | Pending | Pending | Pending | Completed | Pending | High | Back & DB Completed | Backend | Database integrated
8 | Reports | Reports | Generate reports | Pending | Pending | Pending | Pending | Pending | Medium | Not Started | Team | Pending
9 | Examination | Exam Module | Manage examinations | Pending | Pending | Pending | Pending | Pending | High | Not Started | Team | Pending
10 | User Management | User CRUD | Admin can manage users | Pending | Completed | Pending | Completed | Pending | High | Backend Completed | Backend | CRUD APIs completed
11 | User Management | Account Activate/Deactivate | Admin can activate/deact | Pending | Completed | Pending | Completed | Pending | High | Backend Completed | Backend | Security enforced
12 | Authentication | JWT Authentication | Secure user authentication | Pending | Completed | Pending | Pending | Pending | Critical | Backend Completed | Backend | JWT implemented
13 | Authentication | Password Encryption | Secure password storage | Pending | Completed | Pending | Pending | Pending | Critical | Backend Completed | Backend | bcrypt implemented
14 | Authentication | RBAC | Restrict access based on roles | Pending | Completed | Pending | Completed | Pending | Critical | Backend Completed | Backend | RBAC integrated
15 | Assignment | Assignment Management | Admin manage assignments | Pending | Completed | Pending | Completed | Pending | High | Back & DB Completed | Backend | CRUD + DB completed
16 | Assignment Submission | Submit Assignment | Students submit assignments | Pending | Pending | Pending | Completed | Pending | High | Database Completed | Database | Table & RLS completed
17 | Assignment Submission | Submission APIs | Assignment submission APIs | Pending | In Progress | Pending | Pending | Pending | High | In Progress | Backend | Structure completed
18 | Notifications | Notification Module | Send/View notifications | Pending | Completed | Pending | Completed | Pending | High | Back & DB Completed | Backend | Fully completed
19 | Reports & Analytics | Attendance Reports | Generate attendance reports | Pending | In Progress | Pending | Pending | Pending | Medium | In Progress | Backend | Module initialized
20 | Reports & Analytics | Dashboard Reports | Analytics dashboard | Pending | In Progress | Pending | Pending | Pending | Medium | In Progress | Backend | Awaiting DB integration
21 | Teacher Access | Teacher Class Scoping | Teachers access only assigned cls | Pending | In Progress | Pending | Completed | Pending | High | In Progress | Backend | IDOR protection added
22 | Users Database | User Table Enhancement | Support authentication fields | Pending | Pending | Pending | Completed | Pending | High | Database Completed | Database | Auth fields added
23 | Security | Failed Login Tracking | Track failed login attempts | Pending | Pending | Pending | Completed | Pending | Medium | Database Completed | Database | Security enhancement
24 | Security | Principal Permissions | Principal treated as Admin | Pending | Pending | Pending | Completed | Pending | High | Database Completed | Database | Permissions updated